## RAID Log
RAID LOG
Risks · Assumptions · Issues · Dependencies · Decisions — Client Onboarding
Project: [CLIENT NAME] — [project name pilot] |  | PM / Owner: [Name] |  | Last Updated: [DD/MM/YYYY] |  | Open Items: =COUNTIF(H10:H500,"Open")+COUNTIF(H10:H500,"In Progress")+COUNTIF(H10:H500,"Escalated") |  | Risks Open: =COUNTIFS(B10:B500,"Risk",H10:H500,"Open")
CATEGORY LEGEND |  | ■ Risk | ■ Assumption | ■ Issue | ■ Dependency | ■ Decision | Impact: 🔴 High 🟡 Medium 🟢 Low
📋 PLANNING PHASE — Pre Kick-Off
ID | Category | Description | Impact | Probability / Likelihood | Owner | Target Date | Status | Mitigation / Action | Notes / History
P-001 | Risk | Client infrastructure not ready in time for SW deployment | High | Medium | [PM] | [DD/MM/YYYY] | Open | Agree infrastructure checklist at Kick-Off. Define a readiness sign-off gate before SW delivery. | Flagged during pre-kick-off call. Follow up in WS #2.
P-002 | Assumption | Client team has dedicated availability for workshops and testing phases | High | High | [PM] | [DD/MM/YYYY] | Open | Confirm resource allocation and named individuals at Kick-Off meeting. | Client confirmed SPOC but individual engineer availability TBC.
P-003 | Risk | Key client contact changes during project (SPOC turnover) | Medium | Low | [CRO] | [DD/MM/YYYY] | Open | Document all contacts in Stakeholder Register. Ensure knowledge transfer if change occurs.
P-004 | Dependency | Client must provide test environment access before Phase 1 testing can begin | High | High | [Tech Dir.] | [DD/MM/YYYY] | Open | Confirm environment specs and access credentials by T1. Block testing phases until resolved. | Environment specs shared. Awaiting client confirmation.
P-005 | Assumption | Contract signed and initial invoice paid before project kick-off (T0) | High | High | [CRO] | [DD/MM/YYYY] | Closed | Verified prior to scheduling Kick-Off Meeting. | Confirmed signed 30/06/2025. Invoice paid.
P-006 | Decision | Project will be delivered in 5 consecutive phases as defined in the contract | High | High | [PM] | [DD/MM/YYYY] | Closed | Agreed at contract stage. Phases may be adjusted by Steering Committee only. | Validated at STC #1 (Kick-Off).
P-007 | Risk | Quantum-safe algorithm not yet natively supported by client's existing PKI | Medium | High | [Tech Dir.] | [DD/MM/YYYY] | Open | Assess PKI compatibility during WS #2. Plan hybrid certificate deployment if needed.
🚀 EXECUTION PHASE — Post Kick-Off & Ongoing
ID | Category | Description | Impact | Probability / Likelihood | Owner | Target Date | Status | Mitigation / Action | Notes / History
E-001 | Issue | SW delivery #1 delayed by 3 days due to packaging issue | Medium | — | [Tech Dir.] | [DD/MM/YYYY] | In Progress | Re-packaged Docker container. New delivery date confirmed. Client notified by email. | Raised TCM #1. Resolved 05/09/2025.
E-002 | Risk | Client testing team unfamiliar with Docker — risk of slow setup | Medium | High | [PM] | [DD/MM/YYYY] | Open | Schedule 1h onboarding call on Docker basics before Phase 1 testing starts.
E-003 | Decision | Hybrid certificate deployment agreed for Phase 2 (classical + ML-DSA) | High | — | [Tech Dir.] | [DD/MM/YYYY] | Closed | Decision taken in TCM #1. Architecture diagram updated. | Agreed 15/09/2025. Documented in TCM #1 minutes.
E-004 | Dependency | Phase 3 (gRPC) cannot start until Phase 2 test results validated by client | High | Medium | [PM] | [DD/MM/YYYY] | Open | Add Phase 2 sign-off as gate in project tracker. Confirm with client at TCM #2.
E-005 | Issue | Port 443 not opened on client firewall — blocking REST API tests | High | — | [Client SPOC] | [DD/MM/YYYY] | Open | Escalated to client IT team. CNS provided firewall configuration instructions. | Raised by Tech Director 22/09/2025.
E-006 | Assumption | Client will provide test data sets for signature validation by T2 | Medium | Medium | [PM] | [DD/MM/YYYY] | Open | Confirm format and volume of test data at WS #2. Add to client action log.
E-007 | Risk | Project closure delayed if client does not validate deliverables on time | High | Medium | [CRO] | [DD/MM/YYYY] | Open | Define acceptance SLA in contract. Escalate to Steering Committee if >2 weeks delay.
E-008
E-009
E-010
E-011
E-012
E-013
E-014
E-015

## Dashboard
RAID LOG — DASHBOARD SUMMARY
Live summary — auto-calculated from RAID Log sheet
Category | Total | Open | In Progress | Closed | Escalated | High Impact
Risk | 5 | 5 | 0 | 0 | 0 | 2
Assumption | 3 | 2 | 0 | 1 | 0 | 1
Issue | 2 | 1 | 1 | 0 | 0 | 1
Dependency | 2 | 2 | 0 | 0 | 0 | 2
Decision | 2 | 0 | 0 | 2 | 0 | 0
TOTAL | -443 | 10 | 1 | 3 | 0 | 6
QUICK REFERENCE — WHAT EACH CATEGORY MEANS
Risk | Something that COULD happen and negatively affect the project. Track probability + impact. Define mitigation.
Assumption | Something you are TREATING AS TRUE without confirmed evidence. Must be validated — if wrong, it becomes a Risk or Issue.
Issue | Something that HAS ALREADY happened and is causing a problem RIGHT NOW. Needs immediate action.
Dependency | Something the project RELIES ON from another team, system, or party. If it's late, your work is blocked.
Decision | A formal CHOICE made during the project. Log it so everyone knows what was decided, when, and by whom.