## Communication Matrix
COMMUNICATION PLAN
Company X — Client Onboarding ¦ Who gets what, when, and how
Project: [CLIENT NAME] — Crypto-Agility Pilot |  | PM / Owner: [Name] |  | Version: v1.0 |  | Last Updated: [DD/MM/YYYY]
📌 COMMUNICATION OBJECTIVES
1. Ensure all stakeholders receive the right information at the right time throughout the project lifecycle.
2. Maintain full transparency on project status, risks, decisions, and changes — with no surprises.
3. Separate communication by audience: technical detail for technical teams, executive summary for sponsors.
4. Create a documented record of all formal communications for audit and project closure purposes.
📋 STAKEHOLDER COMMUNICATION MATRIX
# | Stakeholder / Group | Organisation | Information Needed | Frequency | Channel | Format | Owner | Timing / Trigger | Last Sent
CLIENT — EXECUTIVE LEVEL
1 | Project Sponsor | [CLIENT NAME] | Project health, major decisions, milestone completion, budget status | Monthly | Report + Email | Executive Summary Report | [PM / CRO] | 1st week of month | [DD/MM/YYYY]
CLIENT — PROJECT LEVEL
2 | Client SPOC / Project Lead | [CLIENT NAME] | Full project status, action log, risks, upcoming milestones, decisions | Bi-weekly | Email + Meeting | Status Update Email + TCM Minutes | [PM] | Every 2 weeks — after TCM | [DD/MM/YYYY]
3 | Client Technical Lead | [CLIENT NAME] | Technical delivery details, test plans, SW release notes, environment issues | As needed + Monthly | Chat + Email | Technical notes / TCM agenda | [Tech Dir.] | Before each delivery or test phase | [DD/MM/YYYY]
4 | Client Full Team | [CLIENT NAME] | Meeting invites, agendas, minutes, workshop materials | Per meeting | Email | Meeting invite + Minutes | [PM] | 48h before meeting / 24h after | [DD/MM/YYYY]
Company X— INTERNAL
5 | Project Manager | Company X | Full project view — risks, actions, client feedback, delivery status | Continuous | All channels | All formats | Self | Ongoing | —
6 | Technical Director | Company X | Technical scope, client environment issues, delivery blockers | Weekly | Chat + Email | Internal update + client technical emails | [PM] | Every Monday | —
7 | CRO / Exec Sponsor | Company X | Commercial health, client satisfaction, escalations, closure readiness | Monthly | Email + Meeting | Executive Summary | [PM] | End of month | —
JOINT — BOTH PARTIES
8 | Steering Committee (STC) | Company X+ [CLIENT NAME] | Project governance, major decisions, milestone sign-off, escalations | Per milestone | Meeting | STC Agenda + Minutes + Presentation | [PM] | At each Tn milestone | [DD/MM/YYYY]
9 | Technical Coordination Meeting (TCM) | Company X+ [CLIENT NAME] | Technical progress, delivery status, test results, open issues | Monthly | Video Call | TCM Agenda + Minutes + Action Log | [PM + Tech Dir.] | Mid-month, 30 min | [DD/MM/YYYY]
10 | All Stakeholders — Escalation | Company X + [CLIENT NAME] | Urgent issue, blocker, or risk requiring immediate attention | Ad-hoc | Email + Phone | Escalation email + follow-up call | [PM / CRO] | Within 24h of issue identification | [DD/MM/YYYY]

## Meetings & Reporting
MEETINGS & REPORTING GUIDE
Standard meeting types, objectives, and reporting formats for this project
Project: [CLIENT NAME] — Crypto-Agility Pilot |  | PM / Owner: [Name] |  | Version: v1.0 |  | Last Updated: [DD/MM/YYYY]
📅 STANDARD MEETING TYPES
Meeting Type | Objective | Participants | Frequency | Duration | Owner / Facilitator
Kick-Off Meeting (STC #1) | Launch the project. Align on scope, roles, plan, and governance. First formal sign-off. | All stakeholders — CNS + Client | Once — project start | 2–3 hours | CNS PM
Steering Committee (STC) | Governance checkpoint at each major milestone. Review progress, approve changes, resolve escalations. | Sponsors + PMs both sides | At each Tn milestone | 1–1.5 hours | CNS PM
Technical Coordination Meeting (TCM) | Monthly technical sync. Delivery status, test results, open issues, next steps. | Technical teams both sides + PMs | Monthly — mid-month | 30 minutes | CNS PM + Tech Dir.
Workshop #1 — Fundamentals | Introduce PQC principles, NIST standards, CNS architecture, and Phase 1 deliverables. | Client technical + management team | Once — before T1 | 2.5 hours | CNS Tech Dir.
Workshop #2 — Test Plan Scoping | Define test objectives, methods, success criteria, and test book. Agree acceptance process. | Technical teams both sides | Once — around T1 | 2.5 hours | CNS Tech Dir.
Workshop #3 — Results Analysis | Joint review of PoC results. Analyse findings, discuss production implications, fuel closure report. | All stakeholders | Once — around T4 | 3 hours | CNS Tech Dir. + PM
Ad-hoc / On-demand Meeting | Address urgent technical or commercial issue that cannot wait for next scheduled meeting. | Relevant parties only | As needed | 30–60 minutes | Requesting party
Project Closure Meeting (STC #last) | Formal project closure. Review all deliverables, sign off, present recommendations, debrief. | All stakeholders — CNS + Client | Once — project end | 1.5–2 hours | CNS PM + CRO
💬 COMMUNICATION CHANNELS — WHEN TO USE WHAT
Channel | Use For | Not For | Response Expected | Formality | Documented?
💬 Chat (Slack / Teams / Telegram) | Quick technical questions, informal coordination, sharing files, daily check-ins | Decisions, approvals, formal status, anything that needs an audit trail | Same day | Informal | ❌ No — follow up by email if decision reached
📧 Email | Status updates, meeting summaries, formal notifications, action confirmations, CR submissions | Urgent issues (use phone), casual questions (use chat) | Within 24–48h | Semi-formal | ✅ Yes — always
📊 Monthly Report | Executive-level summary of project health: milestones, KPIs, risks, financials | Day-to-day operational detail | Acknowledgement within 3 days | Formal | ✅ Yes — filed in project folder
📹 Video Call / TCM | Monthly technical review, workshops, problem-solving sessions requiring discussion | Simple status updates that can be an email | N/A — live meeting | Semi-formal | ✅ Yes — minutes sent within 24h
🤝 In-person Meeting / STC | Kick-off, milestone steering, workshops, project closure | Routine updates | N/A — live meeting | Formal | ✅ Yes — minutes + presentation filed
📞 Phone / Urgent Call | Escalations, blockers, urgent decisions that cannot wait for next scheduled touchpoint | Routine communication | Immediate | Informal | ⚠️ Follow up in writing within 2h
📈 REPORTING CADENCE & FORMATS
Report / Update | Audience | Frequency | Format / Template | Owner | Distribution
Post-Meeting Action Email | All meeting attendees | Within 24h of every meeting | Plain email — subject: [PROJECT] Actions [DATE] List: action, owner, due date | [PM] | Reply-all to meeting invite thread
TCM Minutes | Client SPOC + technical leads + CNS team | Monthly — within 24h of TCM | Meeting Notes Template (.xlsx) Attached to email | [PM] | Email to all TCM attendees
Bi-weekly Status Update | Client SPOC + PM both sides | Every 2 weeks | Short email — 5 lines max: % complete · actions due · risks · next milestone | [PM] | Direct email to SPOC
Monthly Executive Report | Sponsors + CRO both sides | 1st week of each month | 1-page PDF or email summary: Milestone status · KPIs · top 3 risks · financials | [PM + CRO] | Email to sponsors
Delivery Notification | Client SPOC + Technical Lead | At each SW delivery | Email with: what was delivered · version · installation instructions · acceptance deadline | [Tech Dir. + PM] | Email + confirmation reply requested
Project Closure Report | All stakeholders | Once — at project end | Formal document: results summary · KPIs achieved · lessons learned · recommendations | [PM + Tech Dir.] | Presented at STC closure meeting + emailed

## Status Update Template
BI-WEEKLY STATUS UPDATE TEMPLATE
Copy this template into your email body every two weeks — keep it under 1 page
Project: [CLIENT NAME] — Crypto-Agility Pilot |  | PM / Owner: [Name] | Version: v1.0 | Last Updated: [DD/MM/YYYY]
📌 HOW TO USE — send as email body every 2 weeks to Client SPOC
Subject line: [PROJECT NAME] — Status Update [DD/MM/YYYY] To: Client SPOC CC: CNS PM, Tech Dir., CRO Rule: keep it short. If it needs more than 5 sections → call instead.
🚦 PROJECT HEALTH INDICATOR
🟢 ON TRACK |  | All milestones on schedule. No critical issues.
🟡 AT RISK |  | One or more risks may impact timeline or scope. Monitoring closely.
🔴 OFF TRACK |  | Active issue impacting delivery. Escalation or recovery plan in place.
✉️ EMAIL TEMPLATE — COPY & FILL IN
🚦 Overall Status | [🟢 On Track / 🟡 At Risk / 🔴 Off Track] [One sentence on why.]
✅ Completed Since Last Update | • [What was delivered, tested, or closed in the last 2 weeks] • [Meeting held / minutes sent / action closed] • [Any deliverable accepted by client]
📅 Upcoming in Next 2 Weeks | • [Next milestone or delivery] • [Scheduled meeting — TCM / workshop] • [Action due from client or CNS]
⚠️ Risks & Issues (if any) | • [Risk or issue — one line each] • [Owner and mitigation action] • Leave blank if nothing to flag — do not write 'None' unnecessarily
📋 Actions Required from Client | • [Specific ask — be direct. Owner. Due date.] • Example: Please confirm test environment readiness by [date] • Example: Awaiting acceptance sign-off on Delivery #2
📎 Attachments (if any) | • [TCM minutes / Action log / Delivery note / Change request] • Keep to one attachment per update where possible